## 150-Project Portfolio
Task ID | Project Name | Task Title | Sprint | Owner / Project Manager | Department | Priority | Status | Progress (%) | Estimated Hours | Actual Hours | Allocated Budget ($) | Actual Spend ($) | Variance ($) | Start Date | Due Date | Risk Level | Team Members | Blocker Details
TASK-001 | Nexus Cloud Core | Distributed Multi-Region Redis Cluster & Invalidation Shield (Part 1) | Sprint 20 | David Kim | Backend Architecture | Critical | Blocked | 8 | 40 | 4 | 15000 | 1500 | -13500 | 2026-08-10 | 2026-10-05 | Critical | 2 | Awaiting InfoSec compliance sign-off
TASK-002 | FinTech Payment Hub | PCI DSS v4.0 HSM Key Management & Token Vault Rotation (Part 2) | Sprint 20 | Priya Sharma | Data Science | Critical | Blocked | 12 | 50 | 8 | 20000 | 3000 | -17000 | 2026-08-11 | 2026-10-06 | Critical | 3 | Vendor integration failure on payment webhook
TASK-003 | AI Predictive Engine | Zero-Downtime PostgreSQL Schema Migration with pg_repack (Part 3) | Sprint 20 | Marcus Brody | DevSecOps | Critical | In Progress | 15 | 60 | 12 | 25000 | 4688 | -20312 | 2026-08-12 | 2026-10-07 | Critical | 4 | None
TASK-004 | CyberSec Zero-Trust Guard | High-Throughput Kafka Partition Rebalance & MirrorMaker Sync (Part 4) | Sprint 20 | Alex Rivera | Frontend Engineering | Critical | Blocked | 18 | 70 | 16 | 30000 | 6750 | -23250 | 2026-08-13 | 2026-10-08 | Critical | 5 | Third-party OAuth2 identity provider outage
TASK-005 | Omnichannel Mobile Suite | Real-Time Fraud Detection LightGBM Inference Microservice (Part 1) | Sprint 20 | Elena Rostova | Quality Assurance | Critical | Blocked | 20 | 80 | 21 | 35000 | 8750 | -26250 | 2026-08-14 | 2026-10-09 | Critical | 6 | Pending legal sign-off on GDPR data transfer agreement
TASK-006 | Data Lakehouse 2.0 | Multi-Gateway Stripe & Adyen Automatic Failover Router (Part 2) | Sprint 20 | James Wilson | Mobile Development | Critical | Completed | 22 | 90 | 26 | 40000 | 11000 | -29000 | 2026-08-15 | 2026-10-10 | Critical | 7 | None
TASK-007 | Customer Portal 360 | OAuth2.1 & OpenID Connect PKCE Identity Federation Layer (Part 3) | Sprint 20 | Carlos Mendez | Infrastructure & Cloud | Critical | Blocked | 24 | 100 | 31 | 45000 | 13500 | -31500 | 2026-08-16 | 2026-10-11 | Low | 2 | Hardware accelerator / GPU quota allocation denied in us-east-1
TASK-008 | Edge IoT Telemetry Platform | FastAPI & ONNX Runtime Model Serving with CUDA Acceleration (Part 4) | Sprint 20 | Maya Lin | DevSecOps | Critical | Blocked | 25 | 110 | 36 | 50000 | 15625 | -34375 | 2026-08-17 | 2026-10-12 | Critical | 3 | API rate limit exceeded on enterprise clearinghouse gateway
TASK-009 | Nexus Cloud Core | Automated Feature Store Ingestion & Validation Pipeline (Part 1) | Sprint 20 | Tariq Vance | Data Science | Critical | Blocked | 27 | 40 | 14 | 55000 | 18563 | -36437 | 2026-08-18 | 2026-10-13 | Critical | 4 | SOC2 Type II penetration testing remediation in progress
TASK-010 | FinTech Payment Hub | mTLS Service-to-Service Encryption with Envoy Sidecars (Part 2) | Sprint 20 | Sophia Chen | Product & Design | Critical | In Progress | 28 | 50 | 18 | 60000 | 21000 | -39000 | 2026-08-19 | 2026-10-14 | Low | 5 | None
TASK-011 | AI Predictive Engine | Container Vulnerability Scanning & SBOM Generation Pipeline (Part 3) | Sprint 20 | David Kim | Backend Architecture | Critical | Blocked | 8 | 60 | 6 | 65000 | 6500 | -58500 | 2026-08-10 | 2026-10-15 | Critical | 6 | Unresolved merge collision in core cryptography subsystem
TASK-012 | CyberSec Zero-Trust Guard | Automated Blue-Green Deployment Controller for Kubernetes (Part 4) | Sprint 20 | Priya Sharma | Data Science | Critical | Blocked | 12 | 70 | 11 | 70000 | 10500 | -59500 | 2026-08-11 | 2026-10-16 | Critical | 7 | Staging environment SAN storage hardware failure
TASK-013 | Omnichannel Mobile Suite | Synthetic Data Generator for Anonymized Privacy Shield (Part 1) | Sprint 20 | Marcus Brody | DevSecOps | Critical | In Progress | 15 | 80 | 16 | 15000 | 2813 | -12187 | 2026-08-12 | 2026-10-17 | Critical | 2 | None
TASK-014 | Data Lakehouse 2.0 | Next.js 15 Server Actions & Edge Middleware Caching Layer (Part 2) | Sprint 20 | Alex Rivera | Frontend Engineering | Critical | Blocked | 18 | 90 | 21 | 20000 | 4500 | -15500 | 2026-08-13 | 2026-10-18 | High | 3 | Vendor integration failure on payment webhook
TASK-015 | Customer Portal 360 | Real-Time WebSocket Heartbeat & Connection Recovery Pool (Part 3) | Sprint 20 | Elena Rostova | Quality Assurance | Critical | Blocked | 20 | 100 | 26 | 25000 | 6250 | -18750 | 2026-08-14 | 2026-10-19 | Critical | 4 | Cross-region network partition latency exceeding SLA
TASK-016 | FinTech Payment Hub | Role-Based Access Control (RBAC) Granular Policy Engine (Part 4) | Sprint 21 | James Wilson | Mobile Development | High | Completed | 100 | 110 | 131 | 30000 | 37500 | 7500 | 2026-08-05 | 2026-10-20 | High | 5 | None
TASK-017 | Nexus Cloud Core | Automated Canary Release Routing with Argo Rollouts (Part 1) | Sprint 21 | Carlos Mendez | Infrastructure & Cloud | Critical | In Progress | 71 | 40 | 49 | 35000 | 45500 | 10500 | 2026-08-06 | 2026-10-21 | High | 6 | None
TASK-018 | FinTech Payment Hub | Snowflake Data Warehouse Reverse ETL Streaming Pipeline (Part 2) | Sprint 21 | Maya Lin | DevSecOps | High | In Progress | 72 | 50 | 64 | 40000 | 54000 | 14000 | 2026-08-07 | 2026-10-22 | High | 7 | None
TASK-019 | AI Predictive Engine | GraphQL Federation Gateway Schema Merging & Query Planner (Part 3) | Sprint 21 | Tariq Vance | Data Science | Critical | Completed | 100 | 60 | 80 | 45000 | 63000 | 18000 | 2026-08-08 | 2026-10-23 | High | 2 | None
TASK-020 | FinTech Payment Hub | WebRTC Ultra-Low Latency Audio/Video Streaming Bridge (Part 4) | Sprint 21 | Sophia Chen | Product & Design | High | In Progress | 74 | 70 | 96 | 50000 | 72500 | 22500 | 2026-08-09 | 2026-10-24 | High | 3 | None
TASK-021 | Omnichannel Mobile Suite | Elasticsearch Multi-Cluster Cross-Index Search Optimizer (Part 1) | Sprint 21 | David Kim | Backend Architecture | Critical | In Progress | 75 | 80 | 112 | 55000 | 81400 | 26400 | 2026-08-10 | 2026-10-15 | High | 4 | None
TASK-022 | FinTech Payment Hub | Prometheus & OpenTelemetry Metrics Aggregator Exporter (Part 2) | Sprint 21 | Priya Sharma | Data Science | High | Completed | 100 | 90 | 128 | 60000 | 90000 | 30000 | 2026-08-11 | 2026-10-16 | High | 5 | None
TASK-023 | Customer Portal 360 | Disaster Recovery Cross-Region Snapshot Synchronization (Part 3) | Sprint 21 | Marcus Brody | DevSecOps | Critical | In Progress | 77 | 100 | 131 | 65000 | 89700 | 24700 | 2026-08-12 | 2026-10-17 | High | 6 | None
TASK-024 | FinTech Payment Hub | Mobile Push Notification Orchestration Engine via APNs/FCM (Part 4) | Sprint 21 | Alex Rivera | Frontend Engineering | High | In Progress | 78 | 110 | 148 | 70000 | 99400 | 29400 | 2026-08-13 | 2026-10-18 | High | 7 | None
TASK-025 | Nexus Cloud Core | Automated Playwright End-to-End Regression Test Suite (Part 1) | Sprint 21 | Elena Rostova | Quality Assurance | Critical | Completed | 100 | 40 | 55 | 15000 | 21900 | 6900 | 2026-08-14 | 2026-10-19 | High | 2 | None
TASK-026 | FinTech Payment Hub | Cloud Cost Allocation & Reserved Instance Optimization (Part 2) | Sprint 21 | James Wilson | Mobile Development | High | In Progress | 80 | 50 | 59 | 20000 | 25000 | 5000 | 2026-08-15 | 2026-10-20 | High | 3 | None
TASK-027 | AI Predictive Engine | Idempotent Event Sourcing Ledger for Transaction Audits (Part 3) | Sprint 21 | Carlos Mendez | Infrastructure & Cloud | Critical | In Progress | 81 | 60 | 74 | 25000 | 32500 | 7500 | 2026-08-16 | 2026-10-21 | High | 4 | None
TASK-028 | FinTech Payment Hub | Dynamic Configuration Hot-Reload Daemon with Consul (Part 4) | Sprint 21 | Maya Lin | DevSecOps | High | Completed | 100 | 70 | 90 | 30000 | 40500 | 10500 | 2026-08-17 | 2026-10-22 | High | 5 | None
TASK-029 | Omnichannel Mobile Suite | Terraform Multi-Cloud Infrastructure as Code Module Set (Part 1) | Sprint 21 | Tariq Vance | Data Science | Critical | Blocked | 83 | 80 | 106 | 35000 | 49000 | 14000 | 2026-08-18 | 2026-10-23 | High | 6 | Upstream DB migration schema deadlock on replica
TASK-030 | FinTech Payment Hub | Customer Churn Hazard Prediction Model v3 Deployment (Part 2) | Sprint 21 | Sophia Chen | Product & Design | High | In Progress | 84 | 90 | 124 | 40000 | 58000 | 18000 | 2026-08-19 | 2026-10-24 | High | 7 | None
TASK-031 | Customer Portal 360 | Distributed Multi-Region Redis Cluster & Invalidation Shield (Part 3) | Sprint 22 | David Kim | Backend Architecture | Critical | Completed | 100 | 100 | 141 | 45000 | 66600 | 21600 | 2026-08-05 | 2026-10-15 | High | 2 | None
TASK-032 | FinTech Payment Hub | PCI DSS v4.0 HSM Key Management & Token Vault Rotation (Part 4) | Sprint 22 | Priya Sharma | Data Science | High | In Progress | 86 | 110 | 157 | 50000 | 75000 | 25000 | 2026-08-06 | 2026-10-16 | High | 3 | None
TASK-033 | Nexus Cloud Core | Zero-Downtime PostgreSQL Schema Migration with pg_repack (Part 1) | Sprint 22 | Marcus Brody | DevSecOps | Critical | In Progress | 87 | 40 | 52 | 55000 | 75900 | 20900 | 2026-08-07 | 2026-10-17 | High | 4 | None
TASK-034 | FinTech Payment Hub | High-Throughput Kafka Partition Rebalance & MirrorMaker Sync (Part 2) | Sprint 22 | Alex Rivera | Frontend Engineering | High | Completed | 100 | 50 | 67 | 60000 | 85200 | 25200 | 2026-08-08 | 2026-10-18 | High | 5 | None
TASK-035 | AI Predictive Engine | Real-Time Fraud Detection LightGBM Inference Microservice (Part 3) | Sprint 22 | Elena Rostova | Quality Assurance | Critical | In Progress | 89 | 60 | 83 | 65000 | 94900 | 29900 | 2026-08-09 | 2026-10-19 | High | 6 | None
TASK-036 | FinTech Payment Hub | Multi-Gateway Stripe & Adyen Automatic Failover Router (Part 4) | Sprint 22 | James Wilson | Mobile Development | High | In Progress | 90 | 70 | 83 | 70000 | 87500 | 17500 | 2026-08-10 | 2026-10-20 | High | 7 | None
TASK-037 | Omnichannel Mobile Suite | OAuth2.1 & OpenID Connect PKCE Identity Federation Layer (Part 1) | Sprint 22 | Carlos Mendez | Infrastructure & Cloud | Critical | Completed | 100 | 80 | 99 | 15000 | 19500 | 4500 | 2026-08-11 | 2026-10-21 | High | 2 | None
TASK-038 | FinTech Payment Hub | FastAPI & ONNX Runtime Model Serving with CUDA Acceleration (Part 2) | Sprint 22 | Maya Lin | DevSecOps | High | In Progress | 92 | 90 | 115 | 20000 | 27000 | 7000 | 2026-08-12 | 2026-10-22 | High | 3 | None
TASK-039 | Customer Portal 360 | Automated Feature Store Ingestion & Validation Pipeline (Part 3) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | Blocked | 35 | 75 | 60 | 25000 | 18750 | -6250 | 2026-09-01 | 2026-10-10 | Critical | 4 | Cross-region network partition latency exceeding SLA
TASK-040 | Edge IoT Telemetry Platform | mTLS Service-to-Service Encryption with Envoy Sidecars (Part 4) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 39 | 80 | 64 | 30000 | 22500 | -7500 | 2026-09-01 | 2026-10-11 | High | 5 | None
TASK-041 | Nexus Cloud Core | Container Vulnerability Scanning & SBOM Generation Pipeline (Part 1) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 43 | 85 | 68 | 35000 | 26250 | -8750 | 2026-09-02 | 2026-10-12 | Critical | 6 | None
TASK-042 | FinTech Payment Hub | Automated Blue-Green Deployment Controller for Kubernetes (Part 2) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 47 | 90 | 72 | 40000 | 30000 | -10000 | 2026-09-02 | 2026-10-13 | High | 7 | None
TASK-043 | AI Predictive Engine | Synthetic Data Generator for Anonymized Privacy Shield (Part 3) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 51 | 95 | 76 | 45000 | 33750 | -11250 | 2026-09-03 | 2026-10-14 | Critical | 2 | None
TASK-044 | CyberSec Zero-Trust Guard | Next.js 15 Server Actions & Edge Middleware Caching Layer (Part 4) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 55 | 100 | 80 | 50000 | 37500 | -12500 | 2026-09-03 | 2026-10-15 | High | 3 | None
TASK-045 | Omnichannel Mobile Suite | Real-Time WebSocket Heartbeat & Connection Recovery Pool (Part 1) | Sprint 22 | Sarah Connor | Backend Architecture | Critical | In Progress | 59 | 105 | 84 | 55000 | 41250 | -13750 | 2026-09-04 | 2026-10-16 | Critical | 4 | None
TASK-046 | Data Lakehouse 2.0 | Role-Based Access Control (RBAC) Granular Policy Engine (Part 2) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 63 | 110 | 88 | 60000 | 45000 | -15000 | 2026-09-04 | 2026-10-17 | High | 5 | None
TASK-047 | Customer Portal 360 | Automated Canary Release Routing with Argo Rollouts (Part 3) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 67 | 115 | 92 | 65000 | 48750 | -16250 | 2026-09-05 | 2026-10-18 | Critical | 6 | None
TASK-048 | Edge IoT Telemetry Platform | Snowflake Data Warehouse Reverse ETL Streaming Pipeline (Part 4) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 71 | 120 | 96 | 70000 | 52500 | -17500 | 2026-09-05 | 2026-10-19 | High | 7 | None
TASK-049 | Nexus Cloud Core | GraphQL Federation Gateway Schema Merging & Query Planner (Part 1) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 75 | 125 | 100 | 15000 | 11250 | -3750 | 2026-09-06 | 2026-10-20 | Critical | 2 | None
TASK-050 | FinTech Payment Hub | WebRTC Ultra-Low Latency Audio/Video Streaming Bridge (Part 2) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 79 | 130 | 104 | 20000 | 15000 | -5000 | 2026-09-06 | 2026-10-21 | High | 3 | None
TASK-051 | AI Predictive Engine | Elasticsearch Multi-Cluster Cross-Index Search Optimizer (Part 3) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 83 | 135 | 108 | 25000 | 18750 | -6250 | 2026-09-07 | 2026-10-22 | Critical | 4 | None
TASK-052 | CyberSec Zero-Trust Guard | Prometheus & OpenTelemetry Metrics Aggregator Exporter (Part 4) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 87 | 140 | 112 | 30000 | 22500 | -7500 | 2026-09-07 | 2026-10-23 | High | 5 | None
TASK-053 | Omnichannel Mobile Suite | Disaster Recovery Cross-Region Snapshot Synchronization (Part 1) | Sprint 23 | Sarah Connor | Backend Architecture | Critical | In Progress | 91 | 145 | 116 | 35000 | 26250 | -8750 | 2026-09-08 | 2026-10-24 | Critical | 6 | None
TASK-054 | Data Lakehouse 2.0 | Mobile Push Notification Orchestration Engine via APNs/FCM (Part 2) | Sprint 23 | Alex Rivera | Frontend Engineering | High | In Progress | 45 | 90 | 122 | 40000 | 44000 | 4000 | 2026-08-01 | 2026-09-15 | High | 7 | None
TASK-055 | Customer Portal 360 | Automated Playwright End-to-End Regression Test Suite (Part 3) | Sprint 23 | Elena Rostova | Quality Assurance | High | In Progress | 51 | 100 | 140 | 45000 | 49500 | 4500 | 2026-08-02 | 2026-09-16 | High | 2 | None
TASK-056 | Edge IoT Telemetry Platform | Cloud Cost Allocation & Reserved Instance Optimization (Part 4) | Sprint 23 | James Wilson | Mobile Development | High | In Progress | 57 | 110 | 160 | 50000 | 55000 | 5000 | 2026-08-03 | 2026-09-17 | High | 3 | None
TASK-057 | Nexus Cloud Core | Idempotent Event Sourcing Ledger for Transaction Audits (Part 1) | Sprint 23 | Carlos Mendez | Infrastructure & Cloud | High | In Progress | 63 | 40 | 60 | 55000 | 60500 | 5500 | 2026-08-04 | 2026-09-18 | High | 4 | None
TASK-058 | FinTech Payment Hub | Dynamic Configuration Hot-Reload Daemon with Consul (Part 2) | Sprint 23 | Maya Lin | DevSecOps | High | In Progress | 69 | 50 | 78 | 60000 | 66000 | 6000 | 2026-08-05 | 2026-09-19 | High | 5 | None
TASK-059 | AI Predictive Engine | Terraform Multi-Cloud Infrastructure as Code Module Set (Part 3) | Sprint 23 | Tariq Vance | Data Science | High | Completed | 45 | 60 | 96 | 65000 | 71500 | 6500 | 2026-08-06 | 2026-09-20 | High | 6 | None
TASK-060 | CyberSec Zero-Trust Guard | Customer Churn Hazard Prediction Model v3 Deployment (Part 4) | Sprint 23 | Sophia Chen | Product & Design | High | In Progress | 51 | 70 | 116 | 70000 | 77000 | 7000 | 2026-08-07 | 2026-09-21 | High | 7 | None
TASK-061 | Omnichannel Mobile Suite | Distributed Multi-Region Redis Cluster & Invalidation Shield (Part 1) | Sprint 24 | David Kim | Backend Architecture | High | In Progress | 57 | 80 | 136 | 15000 | 16500 | 1500 | 2026-08-08 | 2026-09-22 | High | 2 | None
TASK-062 | Data Lakehouse 2.0 | PCI DSS v4.0 HSM Key Management & Token Vault Rotation (Part 2) | Sprint 24 | Priya Sharma | Data Science | High | In Progress | 63 | 90 | 158 | 20000 | 22000 | 2000 | 2026-08-09 | 2026-09-23 | High | 3 | None
TASK-063 | Customer Portal 360 | Zero-Downtime PostgreSQL Schema Migration with pg_repack (Part 3) | Sprint 24 | Marcus Brody | DevSecOps | High | In Progress | 69 | 100 | 180 | 25000 | 27500 | 2500 | 2026-08-10 | 2026-09-24 | High | 4 | None
TASK-064 | Edge IoT Telemetry Platform | High-Throughput Kafka Partition Rebalance & MirrorMaker Sync (Part 4) | Sprint 24 | Alex Rivera | Frontend Engineering | High | In Progress | 45 | 110 | 149 | 30000 | 33000 | 3000 | 2026-08-01 | 2026-09-25 | High | 5 | None
TASK-065 | Nexus Cloud Core | Real-Time Fraud Detection LightGBM Inference Microservice (Part 1) | Sprint 24 | Elena Rostova | Quality Assurance | High | In Progress | 51 | 40 | 56 | 35000 | 38500 | 3500 | 2026-08-02 | 2026-09-26 | High | 6 | None
TASK-066 | FinTech Payment Hub | Multi-Gateway Stripe & Adyen Automatic Failover Router (Part 2) | Sprint 24 | James Wilson | Mobile Development | High | In Progress | 57 | 50 | 73 | 40000 | 44000 | 4000 | 2026-08-03 | 2026-09-15 | High | 7 | None
TASK-067 | AI Predictive Engine | OAuth2.1 & OpenID Connect PKCE Identity Federation Layer (Part 3) | Sprint 24 | Carlos Mendez | Infrastructure & Cloud | High | In Progress | 63 | 60 | 90 | 45000 | 49500 | 4500 | 2026-08-04 | 2026-09-16 | High | 2 | None
TASK-068 | CyberSec Zero-Trust Guard | FastAPI & ONNX Runtime Model Serving with CUDA Acceleration (Part 4) | Sprint 24 | Maya Lin | DevSecOps | High | In Progress | 69 | 70 | 109 | 50000 | 55000 | 5000 | 2026-08-05 | 2026-09-17 | High | 3 | None
TASK-069 | Omnichannel Mobile Suite | Automated Feature Store Ingestion & Validation Pipeline (Part 1) | Sprint 24 | Tariq Vance | Data Science | High | Completed | 100 | 80 | 74 | 55000 | 51700 | -3300 | 2026-07-05 | 2026-08-15 | Low | 4 | None
TASK-070 | Data Lakehouse 2.0 | mTLS Service-to-Service Encryption with Envoy Sidecars (Part 2) | Sprint 24 | Sophia Chen | Product & Design | Medium | Completed | 100 | 90 | 85 | 60000 | 57300 | -2700 | 2026-07-07 | 2026-08-17 | Low | 5 | None
TASK-071 | Customer Portal 360 | Container Vulnerability Scanning & SBOM Generation Pipeline (Part 3) | Sprint 24 | David Kim | Backend Architecture | High | Completed | 100 | 100 | 96 | 65000 | 63050 | -1950 | 2026-07-09 | 2026-08-19 | Low | 6 | None
TASK-072 | Edge IoT Telemetry Platform | Automated Blue-Green Deployment Controller for Kubernetes (Part 4) | Sprint 24 | Priya Sharma | Data Science | Medium | Completed | 100 | 110 | 108 | 70000 | 68950 | -1050 | 2026-07-11 | 2026-08-21 | Low | 7 | None
TASK-073 | Nexus Cloud Core | Synthetic Data Generator for Anonymized Privacy Shield (Part 1) | Sprint 24 | Marcus Brody | DevSecOps | High | Completed | 100 | 40 | 40 | 15000 | 15000 | 0 | 2026-07-13 | 2026-08-23 | Low | 2 | None
TASK-074 | FinTech Payment Hub | Next.js 15 Server Actions & Edge Middleware Caching Layer (Part 2) | Sprint 24 | Alex Rivera | Frontend Engineering | Medium | Blocked | 75 | 50 | 38 | 20000 | 14250 | -5750 | 2026-08-15 | 2026-10-20 | Low | 3 | Awaiting InfoSec compliance sign-off
TASK-075 | AI Predictive Engine | Real-Time WebSocket Heartbeat & Connection Recovery Pool (Part 3) | Sprint 24 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 60 | 49 | 25000 | 19475 | -5525 | 2026-08-16 | 2026-10-21 | Low | 4 | None
TASK-076 | CyberSec Zero-Trust Guard | Role-Based Access Control (RBAC) Granular Policy Engine (Part 4) | Sprint 25 | James Wilson | Mobile Development | Medium | In Progress | 89 | 70 | 62 | 30000 | 25365 | -4635 | 2026-08-17 | 2026-10-22 | Medium | 5 | None
TASK-077 | Omnichannel Mobile Suite | Automated Canary Release Routing with Argo Rollouts (Part 1) | Sprint 25 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 80 | 0 | 35000 | 0 | -35000 | 2026-10-18 | 2026-12-18 | Low | 6 | None
TASK-078 | Data Lakehouse 2.0 | Snowflake Data Warehouse Reverse ETL Streaming Pipeline (Part 2) | Sprint 25 | Maya Lin | DevSecOps | Medium | Planned | 0 | 90 | 0 | 40000 | 0 | -40000 | 2026-10-19 | 2026-12-19 | Low | 7 | None
TASK-079 | Customer Portal 360 | GraphQL Federation Gateway Schema Merging & Query Planner (Part 3) | Sprint 25 | Tariq Vance | Data Science | High | Completed | 100 | 100 | 92 | 45000 | 42300 | -2700 | 2026-07-05 | 2026-08-15 | Low | 2 | None
TASK-080 | Edge IoT Telemetry Platform | WebRTC Ultra-Low Latency Audio/Video Streaming Bridge (Part 4) | Sprint 25 | Sophia Chen | Product & Design | Medium | Completed | 100 | 110 | 103 | 50000 | 47750 | -2250 | 2026-07-07 | 2026-08-17 | Low | 3 | None
TASK-081 | Nexus Cloud Core | Elasticsearch Multi-Cluster Cross-Index Search Optimizer (Part 1) | Sprint 25 | David Kim | Backend Architecture | High | Completed | 100 | 40 | 38 | 55000 | 53350 | -1650 | 2026-07-09 | 2026-08-19 | Low | 4 | None
TASK-082 | FinTech Payment Hub | Prometheus & OpenTelemetry Metrics Aggregator Exporter (Part 2) | Sprint 25 | Priya Sharma | Data Science | Medium | Completed | 100 | 50 | 49 | 60000 | 59100 | -900 | 2026-07-11 | 2026-08-21 | Low | 5 | None
TASK-083 | AI Predictive Engine | Disaster Recovery Cross-Region Snapshot Synchronization (Part 3) | Sprint 25 | Marcus Brody | DevSecOps | High | Completed | 100 | 60 | 60 | 65000 | 65000 | 0 | 2026-07-13 | 2026-08-23 | Low | 6 | None
TASK-084 | CyberSec Zero-Trust Guard | Mobile Push Notification Orchestration Engine via APNs/FCM (Part 4) | Sprint 25 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 70 | 53 | 70000 | 49875 | -20125 | 2026-08-15 | 2026-10-20 | Low | 7 | None
TASK-085 | Omnichannel Mobile Suite | Automated Playwright End-to-End Regression Test Suite (Part 1) | Sprint 25 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 80 | 66 | 15000 | 11685 | -3315 | 2026-08-16 | 2026-10-21 | Low | 2 | None
TASK-086 | Data Lakehouse 2.0 | Cloud Cost Allocation & Reserved Instance Optimization (Part 2) | Sprint 25 | James Wilson | Mobile Development | Medium | In Progress | 89 | 90 | 80 | 20000 | 16910 | -3090 | 2026-08-17 | 2026-10-22 | Medium | 3 | None
TASK-087 | Customer Portal 360 | Idempotent Event Sourcing Ledger for Transaction Audits (Part 3) | Sprint 25 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 100 | 0 | 25000 | 0 | -25000 | 2026-10-18 | 2026-12-18 | Low | 4 | None
TASK-088 | Edge IoT Telemetry Platform | Dynamic Configuration Hot-Reload Daemon with Consul (Part 4) | Sprint 25 | Maya Lin | DevSecOps | Medium | Planned | 0 | 110 | 0 | 30000 | 0 | -30000 | 2026-10-19 | 2026-12-19 | Low | 5 | None
TASK-089 | Nexus Cloud Core | Terraform Multi-Cloud Infrastructure as Code Module Set (Part 1) | Sprint 25 | Tariq Vance | Data Science | High | Completed | 100 | 40 | 37 | 35000 | 32900 | -2100 | 2026-07-05 | 2026-08-15 | Low | 6 | None
TASK-090 | FinTech Payment Hub | Customer Churn Hazard Prediction Model v3 Deployment (Part 2) | Sprint 25 | Sophia Chen | Product & Design | Medium | Completed | 100 | 50 | 47 | 40000 | 38200 | -1800 | 2026-07-07 | 2026-08-17 | Low | 7 | None
TASK-091 | AI Predictive Engine | Distributed Multi-Region Redis Cluster & Invalidation Shield (Part 3) | Sprint 26 | David Kim | Backend Architecture | High | Completed | 100 | 60 | 58 | 45000 | 43650 | -1350 | 2026-07-09 | 2026-08-19 | Low | 2 | None
TASK-092 | CyberSec Zero-Trust Guard | PCI DSS v4.0 HSM Key Management & Token Vault Rotation (Part 4) | Sprint 26 | Priya Sharma | Data Science | Medium | Completed | 100 | 70 | 69 | 50000 | 49250 | -750 | 2026-07-11 | 2026-08-21 | Low | 3 | None
TASK-093 | Omnichannel Mobile Suite | Zero-Downtime PostgreSQL Schema Migration with pg_repack (Part 1) | Sprint 26 | Marcus Brody | DevSecOps | High | Completed | 100 | 80 | 80 | 55000 | 55000 | 0 | 2026-07-13 | 2026-08-23 | Low | 4 | None
TASK-094 | Data Lakehouse 2.0 | High-Throughput Kafka Partition Rebalance & MirrorMaker Sync (Part 2) | Sprint 26 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 90 | 68 | 60000 | 42750 | -17250 | 2026-08-15 | 2026-10-20 | Low | 5 | None
TASK-095 | Customer Portal 360 | Real-Time Fraud Detection LightGBM Inference Microservice (Part 3) | Sprint 26 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 100 | 82 | 65000 | 50635 | -14365 | 2026-08-16 | 2026-10-21 | Low | 6 | None
TASK-096 | Edge IoT Telemetry Platform | Multi-Gateway Stripe & Adyen Automatic Failover Router (Part 4) | Sprint 26 | James Wilson | Mobile Development | Medium | In Progress | 89 | 110 | 98 | 70000 | 59185 | -10815 | 2026-08-17 | 2026-10-22 | Medium | 7 | None
TASK-097 | Nexus Cloud Core | OAuth2.1 & OpenID Connect PKCE Identity Federation Layer (Part 1) | Sprint 26 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 40 | 0 | 15000 | 0 | -15000 | 2026-10-18 | 2026-12-18 | Low | 2 | None
TASK-098 | FinTech Payment Hub | FastAPI & ONNX Runtime Model Serving with CUDA Acceleration (Part 2) | Sprint 26 | Maya Lin | DevSecOps | Medium | Planned | 0 | 50 | 0 | 20000 | 0 | -20000 | 2026-10-19 | 2026-12-19 | Low | 3 | None
TASK-099 | AI Predictive Engine | Automated Feature Store Ingestion & Validation Pipeline (Part 3) | Sprint 26 | Tariq Vance | Data Science | High | Completed | 100 | 60 | 55 | 25000 | 23500 | -1500 | 2026-07-05 | 2026-08-15 | Low | 4 | None
TASK-100 | CyberSec Zero-Trust Guard | mTLS Service-to-Service Encryption with Envoy Sidecars (Part 4) | Sprint 26 | Sophia Chen | Product & Design | Medium | Completed | 100 | 70 | 66 | 30000 | 28650 | -1350 | 2026-07-07 | 2026-08-17 | Low | 5 | None
TASK-101 | Omnichannel Mobile Suite | Container Vulnerability Scanning & SBOM Generation Pipeline (Part 1) | Sprint 26 | David Kim | Backend Architecture | High | Completed | 100 | 80 | 77 | 35000 | 33950 | -1050 | 2026-07-09 | 2026-08-19 | Low | 6 | None
TASK-102 | Data Lakehouse 2.0 | Automated Blue-Green Deployment Controller for Kubernetes (Part 2) | Sprint 26 | Priya Sharma | Data Science | Medium | Completed | 100 | 90 | 88 | 40000 | 39400 | -600 | 2026-07-11 | 2026-08-21 | Low | 7 | None
TASK-103 | Customer Portal 360 | Synthetic Data Generator for Anonymized Privacy Shield (Part 3) | Sprint 26 | Marcus Brody | DevSecOps | High | Completed | 100 | 100 | 100 | 45000 | 45000 | 0 | 2026-07-13 | 2026-08-23 | Low | 2 | None
TASK-104 | Edge IoT Telemetry Platform | Next.js 15 Server Actions & Edge Middleware Caching Layer (Part 4) | Sprint 26 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 110 | 83 | 50000 | 35625 | -14375 | 2026-08-15 | 2026-10-20 | Low | 3 | None
TASK-105 | Nexus Cloud Core | Real-Time WebSocket Heartbeat & Connection Recovery Pool (Part 1) | Sprint 26 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 40 | 33 | 55000 | 42845 | -12155 | 2026-08-16 | 2026-10-21 | Low | 4 | None
TASK-106 | FinTech Payment Hub | Role-Based Access Control (RBAC) Granular Policy Engine (Part 2) | Sprint 27 | James Wilson | Mobile Development | Medium | In Progress | 89 | 50 | 45 | 60000 | 50730 | -9270 | 2026-08-17 | 2026-10-22 | Medium | 5 | None
TASK-107 | AI Predictive Engine | Automated Canary Release Routing with Argo Rollouts (Part 3) | Sprint 27 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 60 | 0 | 65000 | 0 | -65000 | 2026-10-18 | 2026-12-18 | Low | 6 | None
TASK-108 | CyberSec Zero-Trust Guard | Snowflake Data Warehouse Reverse ETL Streaming Pipeline (Part 4) | Sprint 27 | Maya Lin | DevSecOps | Medium | Planned | 0 | 70 | 0 | 70000 | 0 | -70000 | 2026-10-19 | 2026-12-19 | Low | 7 | None
TASK-109 | Omnichannel Mobile Suite | GraphQL Federation Gateway Schema Merging & Query Planner (Part 1) | Sprint 27 | Tariq Vance | Data Science | High | Completed | 100 | 80 | 74 | 15000 | 14100 | -900 | 2026-07-05 | 2026-08-15 | Low | 2 | None
TASK-110 | Data Lakehouse 2.0 | WebRTC Ultra-Low Latency Audio/Video Streaming Bridge (Part 2) | Sprint 27 | Sophia Chen | Product & Design | Medium | Completed | 100 | 90 | 85 | 20000 | 19100 | -900 | 2026-07-07 | 2026-08-17 | Low | 3 | None
TASK-111 | Customer Portal 360 | Elasticsearch Multi-Cluster Cross-Index Search Optimizer (Part 3) | Sprint 27 | David Kim | Backend Architecture | High | Completed | 100 | 100 | 96 | 25000 | 24250 | -750 | 2026-07-09 | 2026-08-19 | Low | 4 | None
TASK-112 | Edge IoT Telemetry Platform | Prometheus & OpenTelemetry Metrics Aggregator Exporter (Part 4) | Sprint 27 | Priya Sharma | Data Science | Medium | Completed | 100 | 110 | 108 | 30000 | 29550 | -450 | 2026-07-11 | 2026-08-21 | Low | 5 | None
TASK-113 | Nexus Cloud Core | Disaster Recovery Cross-Region Snapshot Synchronization (Part 1) | Sprint 27 | Marcus Brody | DevSecOps | High | Completed | 100 | 40 | 40 | 35000 | 35000 | 0 | 2026-07-13 | 2026-08-23 | Low | 6 | None
TASK-114 | FinTech Payment Hub | Mobile Push Notification Orchestration Engine via APNs/FCM (Part 2) | Sprint 27 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 50 | 38 | 40000 | 28500 | -11500 | 2026-08-15 | 2026-10-20 | Low | 7 | None
TASK-115 | AI Predictive Engine | Automated Playwright End-to-End Regression Test Suite (Part 3) | Sprint 27 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 60 | 49 | 45000 | 35055 | -9945 | 2026-08-16 | 2026-10-21 | Low | 2 | None
TASK-116 | CyberSec Zero-Trust Guard | Cloud Cost Allocation & Reserved Instance Optimization (Part 4) | Sprint 27 | James Wilson | Mobile Development | Medium | In Progress | 89 | 70 | 62 | 50000 | 42275 | -7725 | 2026-08-17 | 2026-10-22 | Medium | 3 | None
TASK-117 | Omnichannel Mobile Suite | Idempotent Event Sourcing Ledger for Transaction Audits (Part 1) | Sprint 27 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 80 | 0 | 55000 | 0 | -55000 | 2026-10-18 | 2026-12-18 | Low | 4 | None
TASK-118 | Data Lakehouse 2.0 | Dynamic Configuration Hot-Reload Daemon with Consul (Part 2) | Sprint 27 | Maya Lin | DevSecOps | Medium | Planned | 0 | 90 | 0 | 60000 | 0 | -60000 | 2026-10-19 | 2026-12-19 | Low | 5 | None
TASK-119 | Customer Portal 360 | Terraform Multi-Cloud Infrastructure as Code Module Set (Part 3) | Sprint 27 | Tariq Vance | Data Science | High | Completed | 100 | 100 | 92 | 65000 | 61100 | -3900 | 2026-07-05 | 2026-08-15 | Low | 6 | None
TASK-120 | Edge IoT Telemetry Platform | Customer Churn Hazard Prediction Model v3 Deployment (Part 4) | Sprint 27 | Sophia Chen | Product & Design | Medium | Blocked | 100 | 110 | 103 | 70000 | 66850 | -3150 | 2026-07-07 | 2026-08-17 | Low | 7 | Awaiting client architecture board security clearance
TASK-121 | Nexus Cloud Core | Distributed Multi-Region Redis Cluster & Invalidation Shield (Part 1) | Sprint 28 | David Kim | Backend Architecture | High | Completed | 100 | 40 | 38 | 15000 | 14550 | -450 | 2026-07-09 | 2026-08-19 | Low | 2 | None
TASK-122 | FinTech Payment Hub | PCI DSS v4.0 HSM Key Management & Token Vault Rotation (Part 2) | Sprint 28 | Priya Sharma | Data Science | Medium | Completed | 100 | 50 | 49 | 20000 | 19700 | -300 | 2026-07-11 | 2026-08-21 | Low | 3 | None
TASK-123 | AI Predictive Engine | Zero-Downtime PostgreSQL Schema Migration with pg_repack (Part 3) | Sprint 28 | Marcus Brody | DevSecOps | High | Completed | 100 | 60 | 60 | 25000 | 25000 | 0 | 2026-07-13 | 2026-08-23 | Low | 4 | None
TASK-124 | CyberSec Zero-Trust Guard | High-Throughput Kafka Partition Rebalance & MirrorMaker Sync (Part 4) | Sprint 28 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 70 | 53 | 30000 | 21375 | -8625 | 2026-08-15 | 2026-10-20 | Low | 5 | None
TASK-125 | Omnichannel Mobile Suite | Real-Time Fraud Detection LightGBM Inference Microservice (Part 1) | Sprint 28 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 80 | 66 | 35000 | 27265 | -7735 | 2026-08-16 | 2026-10-21 | Low | 6 | None
TASK-126 | Data Lakehouse 2.0 | Multi-Gateway Stripe & Adyen Automatic Failover Router (Part 2) | Sprint 28 | James Wilson | Mobile Development | Medium | In Progress | 89 | 90 | 80 | 40000 | 33820 | -6180 | 2026-08-17 | 2026-10-22 | Medium | 7 | None
TASK-127 | Customer Portal 360 | OAuth2.1 & OpenID Connect PKCE Identity Federation Layer (Part 3) | Sprint 28 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 100 | 0 | 45000 | 0 | -45000 | 2026-10-18 | 2026-12-18 | Low | 2 | None
TASK-128 | Edge IoT Telemetry Platform | FastAPI & ONNX Runtime Model Serving with CUDA Acceleration (Part 4) | Sprint 28 | Maya Lin | DevSecOps | Medium | Planned | 0 | 110 | 0 | 50000 | 0 | -50000 | 2026-10-19 | 2026-12-19 | Low | 3 | None
TASK-129 | Nexus Cloud Core | Automated Feature Store Ingestion & Validation Pipeline (Part 1) | Sprint 28 | Tariq Vance | Data Science | High | Completed | 100 | 40 | 37 | 55000 | 51700 | -3300 | 2026-07-05 | 2026-08-15 | Low | 4 | None
TASK-130 | FinTech Payment Hub | mTLS Service-to-Service Encryption with Envoy Sidecars (Part 2) | Sprint 28 | Sophia Chen | Product & Design | Medium | Completed | 100 | 50 | 47 | 60000 | 57300 | -2700 | 2026-07-07 | 2026-08-17 | Low | 5 | None
TASK-131 | AI Predictive Engine | Container Vulnerability Scanning & SBOM Generation Pipeline (Part 3) | Sprint 28 | David Kim | Backend Architecture | High | Completed | 100 | 60 | 58 | 65000 | 63050 | -1950 | 2026-07-09 | 2026-08-19 | Low | 6 | None
TASK-132 | CyberSec Zero-Trust Guard | Automated Blue-Green Deployment Controller for Kubernetes (Part 4) | Sprint 28 | Priya Sharma | Data Science | Medium | Completed | 100 | 70 | 69 | 70000 | 68950 | -1050 | 2026-07-11 | 2026-08-21 | Low | 7 | None
TASK-133 | Omnichannel Mobile Suite | Synthetic Data Generator for Anonymized Privacy Shield (Part 1) | Sprint 28 | Marcus Brody | DevSecOps | High | Completed | 100 | 80 | 80 | 15000 | 15000 | 0 | 2026-07-13 | 2026-08-23 | Low | 2 | None
TASK-134 | Data Lakehouse 2.0 | Next.js 15 Server Actions & Edge Middleware Caching Layer (Part 2) | Sprint 28 | Alex Rivera | Frontend Engineering | Medium | In Progress | 75 | 90 | 68 | 20000 | 14250 | -5750 | 2026-08-15 | 2026-10-20 | Low | 3 | None
TASK-135 | Customer Portal 360 | Real-Time WebSocket Heartbeat & Connection Recovery Pool (Part 3) | Sprint 28 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 100 | 82 | 25000 | 19475 | -5525 | 2026-08-16 | 2026-10-21 | Low | 4 | None
TASK-136 | Edge IoT Telemetry Platform | Role-Based Access Control (RBAC) Granular Policy Engine (Part 4) | Sprint 29 | James Wilson | Mobile Development | Medium | In Progress | 89 | 110 | 98 | 30000 | 25365 | -4635 | 2026-08-17 | 2026-10-22 | Medium | 5 | None
TASK-137 | Nexus Cloud Core | Automated Canary Release Routing with Argo Rollouts (Part 1) | Sprint 29 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 40 | 0 | 35000 | 0 | -35000 | 2026-10-18 | 2026-12-18 | Low | 6 | None
TASK-138 | FinTech Payment Hub | Snowflake Data Warehouse Reverse ETL Streaming Pipeline (Part 2) | Sprint 29 | Maya Lin | DevSecOps | Medium | Planned | 0 | 50 | 0 | 40000 | 0 | -40000 | 2026-10-19 | 2026-12-19 | Low | 7 | None
TASK-139 | AI Predictive Engine | GraphQL Federation Gateway Schema Merging & Query Planner (Part 3) | Sprint 29 | Tariq Vance | Data Science | High | Completed | 100 | 60 | 55 | 45000 | 42300 | -2700 | 2026-07-05 | 2026-08-15 | Low | 2 | None
TASK-140 | CyberSec Zero-Trust Guard | WebRTC Ultra-Low Latency Audio/Video Streaming Bridge (Part 4) | Sprint 29 | Sophia Chen | Product & Design | Medium | Completed | 100 | 70 | 66 | 50000 | 47750 | -2250 | 2026-07-07 | 2026-08-17 | Low | 3 | None
TASK-141 | Omnichannel Mobile Suite | Elasticsearch Multi-Cluster Cross-Index Search Optimizer (Part 1) | Sprint 29 | David Kim | Backend Architecture | High | Completed | 100 | 80 | 77 | 55000 | 53350 | -1650 | 2026-07-09 | 2026-08-19 | Low | 4 | None
TASK-142 | Data Lakehouse 2.0 | Prometheus & OpenTelemetry Metrics Aggregator Exporter (Part 2) | Sprint 29 | Priya Sharma | Data Science | Medium | Completed | 100 | 90 | 88 | 60000 | 59100 | -900 | 2026-07-11 | 2026-08-21 | Low | 5 | None
TASK-143 | Customer Portal 360 | Disaster Recovery Cross-Region Snapshot Synchronization (Part 3) | Sprint 29 | Marcus Brody | DevSecOps | High | Completed | 100 | 100 | 100 | 65000 | 65000 | 0 | 2026-07-13 | 2026-08-23 | Low | 6 | None
TASK-144 | Edge IoT Telemetry Platform | Mobile Push Notification Orchestration Engine via APNs/FCM (Part 4) | Sprint 29 | Alex Rivera | Frontend Engineering | Medium | Blocked | 75 | 110 | 83 | 70000 | 49875 | -20125 | 2026-08-15 | 2026-10-20 | Low | 7 | Awaiting InfoSec compliance sign-off
TASK-145 | Nexus Cloud Core | Automated Playwright End-to-End Regression Test Suite (Part 1) | Sprint 29 | Elena Rostova | Quality Assurance | High | In Progress | 82 | 40 | 33 | 15000 | 11685 | -3315 | 2026-08-16 | 2026-10-21 | Low | 2 | None
TASK-146 | FinTech Payment Hub | Cloud Cost Allocation & Reserved Instance Optimization (Part 2) | Sprint 29 | James Wilson | Mobile Development | Medium | In Progress | 89 | 50 | 45 | 20000 | 16910 | -3090 | 2026-08-17 | 2026-10-22 | Medium | 3 | None
TASK-147 | AI Predictive Engine | Idempotent Event Sourcing Ledger for Transaction Audits (Part 3) | Sprint 29 | Carlos Mendez | Infrastructure & Cloud | Medium | Planned | 0 | 60 | 0 | 25000 | 0 | -25000 | 2026-10-18 | 2026-12-18 | Low | 4 | None
TASK-148 | CyberSec Zero-Trust Guard | Dynamic Configuration Hot-Reload Daemon with Consul (Part 4) | Sprint 29 | Maya Lin | DevSecOps | Medium | Planned | 0 | 70 | 0 | 30000 | 0 | -30000 | 2026-10-19 | 2026-12-19 | Low | 5 | None
TASK-149 | Omnichannel Mobile Suite | Terraform Multi-Cloud Infrastructure as Code Module Set (Part 1) | Sprint 29 | Tariq Vance | Data Science | High | Completed | 100 | 80 | 74 | 35000 | 32900 | -2100 | 2026-07-05 | 2026-08-15 | Low | 6 | None
TASK-150 | Data Lakehouse 2.0 | Customer Churn Hazard Prediction Model v3 Deployment (Part 2) | Sprint 29 | Sophia Chen | Product & Design | Medium | Completed | 100 | 90 | 85 | 40000 | 38200 | -1800 | 2026-07-07 | 2026-08-17 | Low | 7 | None